## Bảng theo dõi tiến độ công việc (hidden)
BẢNG THEO DÕI TIẾN ĐỘ CÔNG VIỆC PHÒNG MARKETING |  |  | 2025-01-01
STT | HẠNG MỤC | NỘI DUNG CHI TIẾT | NGÀY BẮT ĐẦU | DEADLINE | NGÀY HOÀN THÀNH | PIC | TRẠNG THÁI | LINK KẾT QUẢ/SẢN PHẨM | GHI CHÚ
1 | Tìm kiếm khách hàng | Liên hệ 100 khách thông qua Fanpage | 2025-01-01 |  | 2025-01-27 | An | Đã hoàn thành | https://docs.google.com/spreadsheets/d/1CDr5nYgdI5ydfKV90CoS_l_TGmBKwT68s-UvTbFazRk/edit#gid=0 | Liên hệ 100 khách trong đó 30 khách tiềm năng, 50 khách sai nhu cầu, 20 khách chờ xem xét lại
2 | Làm slide báo cáo tuần | Hoàn thành bộ slide báo cáo tuần cho kinh doanh với các trường doanh thu, chi phí, hoạt động, dự kiến,... | 2025-01-01 |  | 2025-01-27 | Bình | Đang chờ duyệt | https://docs.google.com/spreadsheets/d/1CDr5nYgdI5ydfKV90CoS_l_TGmBKwT68s-UvTbFazRk/edit#gid=1 | Dời deadline sang tuần tiếp theo vì bị ảnh hưởng sự kiện cuối năm
Đang thực hiện
Đang thực hiện
Đã hủy
Đang chờ duyệt
Đang thực hiện
Chưa làm
Đang thực hiện
Đã hoàn thành
Todo

## Year 2025
HUMAN RESOURCES WORK PROGRESS TRACKING SHEET |  |  | YEAR 2025
No. | CATEGORY | DETAILED CONTENT | START DATE | DEADLINE | PIC | JANUARY SCORE | FEBRUARY SCORE | MARCH SCORE | APRIL SCORE | MAY SCORE | JUNE SCORE | JULY SCORE | AUGUST SCORE | SEPTEMBER SCORE | OCTOBER SCORE | NOVEMBER SCORE | DECEMBER SCORE | NOTES
JANUARY 2025
1 | Large-scale recruitment | Implement a cross-department recruitment plan for January 2025 | 2025-01-03 | 2025-01-09 | Employee 1 | 1 | [11 empty] | Extend deadline to 09/01/2025
2 | Recruitment support | Post job ads on at least 10 platforms and 20 groups | 2025-01-09 | 2025-01-10 | Employee 1 | 0.8
3 | Recruitment support | Review and classify newly received applicant profiles | 2025-01-10 | 2025-01-12 | Employee 1 | 0
4 | Recruitment support | Prepare interview invitation letters using the company’s standard template | 2025-01-10 | 2025-01-12 | Employee 1 | 0
5 | Human resources processes | Standardize or update human resources department workflows | 2025-01-03 | 2025-01-09 | Employee 2 | 1
6 | Employee records management | Update the current employee list and verify personal information and employment status | 2025-01-10 | 2025-01-12 | Employee 2 | 0
7 | Timekeeping & working hours tracking | Consolidate weekly timesheets from departments | 2025-01-11 | 2025-01-12 | Employee 3 | 0
8 | HR administration | Draft and send internal announcements as requested by management | 2025-01-03 | 2025-01-04 | Employee 1 | 0 | [11 empty] | Manager drafts announcements independently
9 | Payroll & compensation management | Compile payroll, bonus, and allowance data for employees for December 2024 | 2025-01-03 | 2025-01-09 | Employee 1 | 1
10 | Create onboarding training slides | Develop ideas and complete onboarding training slide deck for new employees | 2025-01-03 | 2025-01-05 | Employee 3 | 0.6
11 | Update employee data | Update employee records for changes in accounts, positions, and contracts in Q1 2025 | 2025-01-03 | 2025-01-04 | Employee 1 | 1

## January 2025
HUMAN RESOURCES WORK PROGRESS TRACKING SHEET |  |  | JANUARY 2025
No. | CATEGORY | DETAILED CONTENT | START DATE | DEADLINE | COMPLETION DATE | PIC | DELAY (DAYS) | ACTUAL COMPLETION DAYS | ACTUAL PROGRESS | STATUS | SCORE | WORK QUALITY | OVERALL EVALUATION | NOTES
1 | Large-scale recruitment | Implement a cross-department recruitment plan for January 2025 | 2025-01-03 | 2025-01-09 | 2025-01-09 | Employee 1 | 5.5 | 5.5 | 100% | Completed | 1 | Outstanding | Outstanding | Extend deadline to 09/01/2025
2 | Recruitment support | Post job ads on at least 10 platforms and 20 groups | 2025-01-09 | 2025-01-10 | 2025-01-11 | Employee 1 | 2 | 2.5 | 100% | Completed late | 0.8 | Meets expectations | Below expectations
3 | Recruitment support | Review and classify newly received applicant profiles | 2025-01-10 | 2025-01-12 | Not started | Employee 1 | 1.5 | 0 | 20% | Not started | 0
4 | Recruitment support | Prepare interview invitation letters using the company’s standard template | 2025-01-10 | 2025-01-12 | Not started | Employee 1 | 1.5 | 0 | 0% | In progress | 0
5 | Human resources processes | Standardize or update human resources department workflows | 2025-01-03 | 2025-01-09 | 2025-01-08 | Employee 2 | 5.5 | 4.5 | 70% | Pending approval | 1
6 | Employee records management | Update the current employee list and verify personal information and employment status | 2025-01-10 | 2025-01-12 | Not started | Employee 2 | 1.5 | 0 | 40% | In progress | 0
7 | Timekeeping & working hours tracking | Consolidate weekly timesheets from departments | 2025-01-11 | 2025-01-12 | Not started | Employee 3 | 0.5 | 0 | 40% | In progress | 0
8 | HR administration | Draft and send internal announcements as requested by management | 2025-01-03 | 2025-01-04 | Cancelled | Employee 1 | 1.5 | 0 | 10% | Cancelled | 0 |  |  | Manager drafts announcements independently
9 | Payroll & compensation management | Compile payroll, bonus, and allowance data for employees for December 2024 | 2025-01-03 | 2025-01-09 | 2025-01-08 | Employee 1 | 5.5 | 4.5 | 100% | Completed | 1 | Meets expectations | Outstanding
10 | Create onboarding training slides | Develop ideas and complete onboarding training slide deck for new employees | 2025-01-03 | 2025-01-05 | 2025-01-06 | Employee 3 | 1.5 | 2.5 | 100% | Completed late | 0.6 | Meets expectations | Below expectations
11 | Update employee data | Update employee records for changes in accounts, positions, and contracts in Q1 2025 | 2025-01-03 | 2025-01-04 | 2025-01-04 | Employee 1 | 1.5 | 1.5 | 100% | Completed | 1 | Outstanding | Meets expectations
12
13
[10 empty] | TOTAL SCORE | 5.4
Formulas:
DELAY (DAYS) = [DEADLINE]-[START DATE]+1 - (WEEKNUM([DEADLINE],1)-WEEKNUM([START DATE],1))*1.5 - IF(WEEKDAY([DEADLINE],1)=7,0.5,0)
ACTUAL COMPLETION DAYS = IF( OR([COMPLETION DATE]="Not started",[COMPLETION DATE]="Cancelled",[COMPLETION DATE]="Not completed"), 0, [COMPLETION DATE]-[START DATE]+1 - (WEEKNUM([COMPLETION DATE],1)-WEEKNUM([START DATE],1))*1.5 - IF(WEEKDAY([COMPLETION DATE],1)=7,0.5,0) )

## February 2025
HUMAN RESOURCES WORK PROGRESS TRACKING SHEET |  |  | FEBRUARY 2025
No. | CATEGORY | DETAILED CONTENT | START DATE | DEADLINE | COMPLETION DATE | PIC | DELAY (DAYS) | ACTUAL COMPLETION DAYS | ACTUAL PROGRESS | STATUS | SCORE | WORK QUALITY | OVERALL EVALUATION | NOTES
1 | Large-scale recruitment | Implement a cross-department recruitment plan for January 2025 | 2025-02-03 | 2025-02-09 | 2025-02-09 | Employee 1 | 5.5 | 5.5 | 100% | Completed | 1 | Outstanding | Outstanding | Extend deadline to 09/01/2025
2 | Recruitment support | Post job ads on at least 10 platforms and 20 groups | 2025-02-09 | 2025-02-10 | 2025-02-11 | Employee 1 | 2 | 3 | 100% | Completed late | 0.66667 | Meets expectations | Below expectations
3 | Recruitment support | Review and classify newly received applicant profiles | 2025-02-10 | 2025-02-12 | Not started | Employee 1 | 3 | 0 | 20% | Not started | 0
4 | Recruitment support | Prepare interview invitation letters using the company’s standard template | 2025-02-10 | 2025-02-12 | Not started | Employee 1 | 3 | 0 | 0% | In progress | 0
5 | Human resources processes | Standardize or update human resources department workflows | 2025-02-03 | 2025-02-09 | 2025-02-08 | Employee 2 | 5.5 | 5.5 | 70% | Pending approval | 1
6 | Employee records management | Update the current employee list and verify personal information and employment status | 2025-02-10 | 2025-02-12 | Not started | Employee 2 | 3 | 0 | 40% | In progress | 0
7 | Timekeeping & working hours tracking | Consolidate weekly timesheets from departments | 2025-02-11 | 2025-02-12 | Not started | Employee 3 | 2 | 0 | 40% | In progress | 0
8 | HR administration | Draft and send internal announcements as requested by management | 2025-02-03 | 2025-02-04 | Cancelled | Employee 1 | 2 | 0 | 10% | Cancelled | 0 |  |  | Manager drafts announcements independently
9 | Payroll & compensation management | Compile payroll, bonus, and allowance data for employees for December 2024 | 2025-02-03 | 2025-02-09 | 2025-02-08 | Employee 1 | 5.5 | 5.5 | 100% | Completed | 1 | Meets expectations | Outstanding
10 | Create onboarding training slides | Develop ideas and complete onboarding training slide deck for new employees | 2025-02-03 | 2025-02-05 | 2025-02-06 | Employee 3 | 3 | 4 | 100% | Completed late | 0.75 | Meets expectations | Below expectations
11 | Update employee data | Update employee records for changes in accounts, positions, and contracts in Q1 2025 | 2025-02-03 | 2025-02-04 | 2025-02-04 | Employee 1 | 2 | 2 | 100% | Completed | 1 | Outstanding | Meets expectations
12
13
[10 empty] | TOTAL SCORE | 5.4167
Formulas:
DELAY (DAYS) = [DEADLINE]-[START DATE]+1 - (WEEKNUM([DEADLINE],1)-WEEKNUM([START DATE],1))*1.5 - IF(WEEKDAY([DEADLINE],1)=7,0.5,0)
ACTUAL COMPLETION DAYS = IF( OR([COMPLETION DATE]="Not started",[COMPLETION DATE]="Cancelled",[COMPLETION DATE]="Not completed"), 0, [COMPLETION DATE]-[START DATE]+1 - (WEEKNUM([COMPLETION DATE],1)-WEEKNUM([START DATE],1))*1.5 - IF(WEEKDAY([COMPLETION DATE],1)=7,0.5,0) )